## Sprint 1
| Sprint 1 |  | Xây dựng website hỗ trợ đặt món nhà hàng tiệc cưới
Team 2 - CNTT
STT | Hours available | Member Name | Comments/Notes
1 |  | Lê Thanh Tuấn | Start Date:06-09-2021 |  |  | End task
2 |  | Trần Thanh Hoàng | End Date: 28-09-2021 |  |  | Over time
3 |  | Trần Đức Minh |  |  |  | Late
4 |  | Phan Thanh Vang | Remanning hours |  |  | ahead of schedule
SUM | 184
How to use this:
No. | BACKLOG ID | Task Description (User Story/ User Case Brokendown) |  | Responsible | Status (Not Started In Progress Completed) | Actual | Estimate | Day 1 (06/09/2021) | Day 2 (07/09/2021) | Day 3 (08/09/2021) | Day 4 (09/09/2021) | Day 5 (10/09/2021) | Day 6 (11/09/2021) | Day 7 (12/09/2021) | Day 8 (13/09/2021) | Day 9 (14/09/2021) | Day 10 (15/09/2021) | Day 11 (16/09/2021) | Day 12 (17/09/2021) | Day 13 (18/09/2021) | Day 14 (19/09/2021) | Day 15 (20/09/2021) | Day 16 (21/09//2021) | Day 17 (22/09//2021) | Day 18 (23/09/2021) | Day 19 (24/09/2021) | Day 20 (25/09/2021) | Day 21 (26/09/2021) | Day 22 (27/09/2021) | Day 23 (28/09/2021)
[6 empty] | 165 | 168 | 168 | 160 | 156 | 152 | 144 | 136 | 128 | 125 | 125 | 112 | 104 | 96 | 96 | 88 | 76 | 76 | 72 | 37 | 40 | 32 | 32 | 8 | 0
1 | Planning Meeting Sprint 1 |  |  | All members |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Sprint Backlog 1 |  |  | All members |  | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Design Sprint 1 | Create Prototype |  |  |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create GUI |  |  |  | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Design class diagram |  |  | All members |  | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | U01,U03 | Code chức năng “ Tìm kiếm, Lọc và sắp sản phẩm ” | Code chức năng “ Tìm kiếm, Lọc và sắp sản phẩm ” | Tuấn, Hoàng |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Design Test Case chức năng “ Tìm kiếm, Lọc và sắp món ăn” | Minh |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test chức năng “ Tìm kiếm, Lọc và sắp sản phẩm”. | Vang |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fix Error | All members |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | U02,U04 | Code chức năng “ Xem thông tin chi tiết món ăn, Nút yêu thích" | Code chức năng “ Xem thông tin chi tiết món ăn, Nút yêu thích" | Vang, Minh |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Design Test “Xem thông tin chi tiết món ăn, Nút yêu thích ” | Tuấn |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test chức năng “ Xem thông tin chi tiết món ăn, Nút yêu thích ” | Vang |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fix Error | All members |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | U05,U06 | Code chức năng “ Liên hệ, Chat box ” | Code chức năng “ Liên hệ, Chat box ” | Hoàng , Minh |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Design Test Case chức năng “ Liên hệ, Chat box ” | Vang |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test chức năng “ Liên hệ, Chat box ” | Tuấn |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fix Error | All members |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | U07,U08 | Code chức năng “ Đặt món , đặt hàng ” | Code chức năng “ Đặt món , đặt hàng ” | Tuấn , Hoàng |  | 29 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0
-3
|  |  | Design Test Case chức năng “ Đặt món , đặt hàng ” | Minh |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
|  |  | Test chức năng “ Đặt món , đặt hàng ” | Vang |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  |  | Fix Error | All members |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0
8 | Release Sprint 1 |  |  | All members |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
9 | Sprint 1 Review |  |  | All members |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
[7 empty] | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
[7 empty] | ACTUAL | 168 | 160 | 156 | 152 | 144 | 136 | 128 | 125 | 125 | 112 | 104 | 96 | 96 | 88 | 76 | 76 | 72 | 34 | 40 | 32 | 32 | 8 | 0
[7 empty] | EST | 168 | 160 | 156 | 152 | 144 | 136 | 128 | 125 | 125 | 112 | 104 | 96 | 96 | 88 | 76 | 76 | 72 | 37 | 40 | 32 | 32 | 8 | 0

## Sprint 2
| Sprint 2 |  | Xây dựng website hỗ trợ đặt món nhà hàng tiệc cưới
Team 2 - CNTT
STT | Hours available | Member Name | Comments/Notes |  |  |  | End task
1 |  | Lê Thanh Tuấn | Start Date:28-09-2021 |  |  |  | Over time
2 |  | Trần Thanh Hoàng | End Date: 20-10-2021 |  |  |  | Late
3 |  | Phan Thanh Vang |  |  |  |  | ahead of schedule
4 |  | Trần Đức Minh | Remanning hours
SUM | 48
How to use this:
No. | BACKLOG ID | Task Description (User Story/ User Case Brokendown) |  | Responsible | Status (Not Started In Progress Completed) | Actual | Estimate | Day 1 (28/09/2021) | Day 2 (29/09/2021) | Day 3 (30/09/2021) | Day 4 (01/10/2021) | Day 5 (02/10/2021) | Day 6 (03/10/2021) | Day 7 (04/10/2021) | Day 8 (05/10/2021) | Day 9 (06/10/2021) | Day 10 (07/10/2021) | Day 11 (08/10/2021) | Day 12 (09/10/2021) | Day 13 (10/10/2021) | Day 14 (11/10/2021) | Day 15 (12/10/2021) | Day 16 (13/10/2021) | Day 17 (14/10/2021) | Day 18 (15/10/2021) | Day 19 (16/10/2021) | Day 20 (17/10/2021) | Day 21 (18/10/2021) | Day 22 (19/10/2021) | Day 23 (20/10/2021)
[6 empty] | 187 | 192 | 192 | 184 | 176 | 168 | 168 | 168 | 144 | 144 | 128 | 128 | 120 | 120 | 112 | 112 | 112 | 112 | 70 | 72 | 45 | 40 | 24 | 24 | 0
1 | Planning Meeting Sprint 2 |  |  | All members |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Sprint Backlog 2 |  |  | All members |  | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Design Sprint 2 | Create Prototype |  |  |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create GUI |  |  |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Design class diagram |  |  | All members |  | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | U10, U11, U12 | Code chức năng “ Quản lý tài khoản, Quản lí loại sản phẩm, Quản lí danh sách liên hệ ” | Code chức năng “ Quản lý tài khoản, Quản lí loại sản phẩm, Quản lí danh sách liên hệ ” | Tuấn |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Design Test Case chức năng “ Quản lý tài khoản, Quản lí loại sản phẩm, Quản lí danh sách liên hệ ” | Vang |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Test chức năng “ Quản lý tài khoản, Quản lí loại sản phẩm, Quản lí danh sách liên hệ ” | Minh |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fix Error | All members |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | U09, U13, U14 | Chức năng “Quản lý đơn hàng, thống kê” | Code chức năng “Quản lý đơn hàng, thống kê, đăng nhập” | Tuấn, Minh |  | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-2
|  |  | Design Test Case chức năng “ Quản lý đơn hàng, thống kê, đăng nhập ” | Hoàng |  | 21 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0
-3
|  |  | Test chức năng “ Quản lý đơn hàng, thống kê , đăng nhập” | Hoàng |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
|  |  | Fix Error | All members |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0
8 | Release Sprint 2 |  |  | All members |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
9 | Sprint 2 Review |  |  | All members |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
[7 empty] | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
[7 empty] | ACTUAL | 192 | 184 | 176 | 168 | 168 | 168 | 144 | 144 | 128 | 128 | 120 | 120 | 112 | 112 | 112 | 112 | 68 | 72 | 42 | 40 | 24 | 24 | 0
[7 empty] | EST | 192 | 184 | 176 | 168 | 168 | 168 | 144 | 144 | 128 | 128 | 120 | 120 | 112 | 112 | 112 | 112 | 70 | 72 | 45 | 40 | 24 | 24 | 0